## Slide 1
GRIDWISE LAB
园区能源
协同优化试点
以 12 周验证峰值控制、设备协同与可复制运营机制
投资决策稿 / 模拟业务数据 / 2026-08-31
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- Hero image: OpenAI built-in image generation; project asset gridwise-energy-control-room.png; generated 2026-08-31.
- All visible business facts are explicitly marked as synthetic.
[/Sources]

## Slide 2
GRIDWISE LAB
现状判断
02
峰值与设备孤岛正在放大能源成本
园区已经具备光伏、储能和分项计量，问题不再是“有没有设备”，而是能否跨系统统一调度。
28.6 GWh
年用电量
模拟基线；用于试点规模判断
8.4 MW
最大需量
夏季工作日峰值；决定削峰价值
3 类
可调资源
光伏、储能、柔性负荷
决策含义：先验证统一调度，再决定是否复制到其他基地。
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- 28.6 GWh, 8.4 MW and 3 resource classes are synthetic scenario inputs.
[/Sources]

## Slide 3
GRIDWISE LAB
方案闭环
03
统一数据与控制闭环是试点的核心
叠加协同层，不替换已有设备控制系统；每一步都保留人工接管与审计记录。
01
采集
计量、气象、设备状态
02
预测
次日负荷与光伏出力
03
优化
需量、电价、生产约束
04
执行
储能与柔性负荷策略
05
复盘
收益、偏差、异常解释
工程目标：可回退、可审计、可复制
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- The five-stage operating loop is a design proposal for the synthetic pilot.
[/Sources]

## Slide 4
GRIDWISE LAB
负荷结构
04
两类负荷贡献了 73% 的用电基线
Chart: 
| 工艺设备 | 暖通空调 | 空压系统 | 辅助系统 | 线损与其他
用电占比 | 52 | 21 | 14 | 9 | 4
73%
工艺设备 + 暖通空调
优先优化工艺排程与冷站联动。
储能只负责削峰，不替代效率改造。
模拟负荷结构｜单位：%
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- Load mix values 52/21/14/9/4 sum to 100% and are synthetic.
[/Sources]

## Slide 5
GRIDWISE LAB
经济性门槛
05
72 万元试点换取三项可验证收益
所有收益都是门槛，不是承诺值；三项同时满足，才进入规模化。
72 万元
试点投入
数据接入、策略引擎、现场服务
≥ 8%
节电门槛
按天气与产量归一化
≥ 12%
削峰门槛
以最大需量口径核算
≤ 12 月
回收期门槛
通过后才复制
模拟测算：预计年化收益 235 万元，静态回收期约 3.7 个月
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- 72万元, 8%, 12%, 12 months, 235万元 and 3.7 months are synthetic scenario calculations.
[/Sources]

## Slide 6
GRIDWISE LAB
实施路线
06
12 周按四个决策门推进
每个阶段都有证据包；任何安全或生产约束不满足，都可退回观察模式。
01
第 1–2 周
基线
确认数据质量、计量边界与收益口径
02
第 3–5 周
影子运行
只给建议，不下发控制
03
第 6–9 周
受控执行
限定设备与时段，逐步扩大覆盖
04
第 10–12 周
对照评估
归一化核算并完成复制建议
第 12 周只做一个决定：复制、延长验证，或停止。
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- The 12-week phase sequence is a synthetic implementation plan.
[/Sources]

## Slide 7
GRIDWISE LAB
治理边界
07
三条护栏让试点不干扰生产
01
权限护栏
只开放白名单设备与限定时段
02
回退护栏
异常时 60 秒内切回原控制逻辑
03
核算护栏
天气、产量和班次归一化后再认定收益
OPERATING CONTROL
运营负责人
拥有最终控制权
自动策略不是唯一通道。
上线前冻结权限、回退与核算口径。
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- The 60-second rollback target is a synthetic governance requirement.
[/Sources]

## Slide 8
GRIDWISE LAB
决策请求
08
建议批准 72 万元受控试点
批准
目标不是做出漂亮看板，
而是证明能源协同能在生产约束内持续运营。
业务负责人
园区运营总监
本次决策
批准试点预算与跨部门资源
下一检查点
第 5 周影子运行评审
批准后两周内完成基线确认，第五周提交首个继续 / 停止决策包
Notes: [Sources]
- Scenario metrics and calculations: synthetic data authored for the Dashi PPT Skill research sample, 2026-08-31.
- The approval amount and checkpoints are synthetic scenario parameters.
[/Sources]